## Home Page
| Solution | Open/Closed
lot of informaiton - | Maybe put in smaller boxes | Open
login | Working | closed
Register option | Working | Closed
Basic functionality of this Page only

## Testing Details
Test# | Description | Details | Owner | Comments | Action
Test1 | Logon Details - Passwork Forgot | Logon Type email Deirdre.Shanahan@gmail.com | Adrian | Allowed me to enter email but did not receive email | Open | Adrian still working to perfection
Test2 | Get onto Meeting Space from logon | Logon as Lisa Sharp Password welcomE01# | Adrian | looks good so far | closed
Test 3 | Check If Edit Profile Works on Meeting Space | Logon as Carol.James@gmail.com password welcomE01# | Adrian | Brought me to meeting space but error because of Profile Screen 2 | closed
Test4 | Check if save working on Edit Profile | Logon as Carol.James@gmail.com password welcomE01# | Adrian | First screen works, second screen display but save not functioning | closed | Working now
test 5 | Edit Porfile of another user | logon as Lisa Sharp- Logon Option/Meeting Space/ Edit profile | Adrian | First screen work , second screen works until I press save and it abends error "Warning: getimagesize(): Filename cannot be empty in C:\Users\User\Documents\GitHub\WebProject\Web\UpdateProfile2.php on line 24" | closed
Test 6 | Edit Profile for Carol James | Logon as Carol.James@gmail.com Password WelcomeE01/Logon Option/Meeting Space/ Edit profile | Adrian | First screen working , second screen works until I Save Get error "Warning: getimagesize(): Filename cannot be empty in C:\Users\User\Documents\GitHub\WebProject\Web\UpdateProfile2.php on line 24" + Notice: Undefined index: check_list in C:\Users\User\Documents\GitHub\WebProject\Web\UpdateProfile2.php on line 62 | closed
Test 7 | select correct partner I want to meet | logon as Lisa Sharp/meeting Space | Adrian | chatting with Paul even though she wants Female ? | open | Deirdre to recheck
Test 8 | mathces found | Logon as Carol.James@gmail.com password welcomE01# | Adrian | You are chatting with No Mathces Found | closed | Need to click on Photo
Test 9 | see if I get the correct sex partner | Logon as Carol.James@gmail.com password welcomE01#/meeting space | Adrian | Matched with Male when she wants a female | closed | Checked again on 28 July - Still showing Male partners
TEst10 | buttons Functon in Meeting space | Logon as Jacob.Newman@gmail.com Password welcomeE01 | Adrian/Mary | none of the buttons in system functional yet | closed | Left Open Selected Like and got error
test11 | check like button | logon as Lisa Sharp and like Angela.Martin | Adrian | worked | Closed
test12 | interested in me test | logon as as Angela.Marting - to check if Test 10 Lisa is someone interetsed in me | Adrian | Angela appears as a match not interested in me | Closed | Lisa Flagged as interested in me
Test13 | remember login details | Logon Details remembering previous emails | Adrian | not remembering Lisa | Closed | Adrian to check
test 14 | select someone I am interetsed in | meeting space select people I may be interested in | Adrian/Mary | allows me to select | closed
test 15 | selected someone I like | Logged on as john.doe@gmail.com and liked Lucas | Adrian/Mary | allowed me to select and view profile | closed
test 16 | view someone I am interested in and like them | Logged on as john.doe@gmail.com select someone I like and view profile and like on view profile | Adrian/Mary | Aborted with error " A session had already been started - ignoring session_start() in C:\Users\User\Documents\GitHub\WebProject\Web\ViewMatchProfile.php on line 18" | Closed
Test 17 | Check if Interetsed in me works | logged on bella.walsh - Una nash interested in me | Adrian | Broke with error | closed | Check Database
Test 18 | check chat funtion |  |  |  | closed | ReDo test
test 19 | Cap off 100KB on Image |  | Adrian/Mary |  | Open
test20 | Admin User needs to go directly to Admin Screen | logon as 16230124@studentmail.ul.ie | Niall | Logged on correctly. Got No Matches Found- Should this be there are no issues found ? Here is printed on left hand page why ? When I select buttons it breaks with error (Screen Shot sent to Niall) | Open
test21 | Admin User need to be able to look at all users reported | logon as 16230124@studentmail.ul.ie | Niall |  | Open
Test22 | admin useer need to be able to supend account | logon as 16230124@studentmail.ul.ie | Niall |  | Open
Test23 | Admins user need to be able to terminate account | logon as 16230124@studentmail.ul.ie | Niall |  | Open
Test24 | Admin need to be able to assign user as administrator | logon as 16230124@studentmail.ul.ie | Niall |  | Open
Test 25 | Admins need to be able view profile and make decisions on same |  | Niall |  | Open
Test26 | reset password |  | Mary |  | Closed
Test27 | sql inection ??? |  | Adrian ?? |  | Open
Test28 | formats the same |  | Mary |  | Open
Test29 | correct all the open tests |  | all |  | Closed
Test30 | Sys Admin - View Profile - |  | Niall |  | closed
Test 32 | Wire up button functions for Like, etc. -> Adrian |  | Adrian |  | Open
Test 33 | Code "Return to Match Profile" -> Adrian |  | Adrian |  | closed
Test 34 | Match Profile - Fix issue with selecting user you are not already matched to |  | Adrian |  | closed
Test 35 | UpdateProfile - Improve Formatting and include Mary's Sliders -> Mary |  | Adrian | Looks Good Left Open until I validate correctly | closed
Test36 | UpdateProfile2 - Improve Formatting |  | Adrian |  | Open
Test37 | Password Reset - Write code -> Adrian |  | Adrian |  | closed | tried again not working 27/7
test38 | Session control - Make sure users cant spoof site -> Adrian |  | Adrian |  | Open
test39 | Chatline - Include bad word logic ->Adrian |  | Adrian |  | Open
Test40 | AdminScreen - Write moderation code -> Nial |  | Niall |  | Open
test41 | more Checks on Meeting Space | Logon as Jacob.Newman@gmail.com Password welcomeE01 | Adrian | Meeting Spaces Showing Matches me with Carol James even though she only wants female partners, Hit View to View Carol Profile. Liked profile and got error | closed | Sent email to team
Test42 | Register new user | Register, Patballycannon@gmail.com , Password submit | Adrian | Got Error Notice: Undefined index: email in C:\Users\User\Documents\GitHub\WebProject\Web\Register.php on line 24 | closed | Adrian to check on 28 April
Test 43 | Logon on throughHIVE - | Lisa.sharp@gmail.com | Adrian ?? | Bringing me to meeting space - no photos for matches and duplicate buttons Like Like http://hive.csis.ul.ie/4065/group05/MeetingSpace.php | Closed
Test 44 | Seeking Age Profile | Lisa Sharp - Seking Age Profile. Saved details. When in again Age is not saved on slider http://hive.csis.ul.ie/4065/group05/UpdateProfile.php | Mary |  | Closed | Slide bar always defaults back . Deirdre to put in Doc
test 44 | Check Age Slider - New uSer | PatBallycannon | Mary | Logged in ok but allowed me to edit profile and put in from 40 to 20 for seeking age | closed
test45 | Can App remember email when I go back from Meeting space | Carol.James@gmail.com password welcomE01#/meeting space | Adrian | does not remember email when I go back to site | closed
Test46 | View Profile of a match | Logged on as Carol James. Selected Jacob Newman - Minumun details appeared | Adrian | Deirdre to check Jacob Newman profile | closed | DO this evening 28/7
Test47 | Meeting Space- How it Works |  |  | What does this do - need more details | closed
test48 | New User | Registered Deirdre1Shanahn. | Adrian/Mary | DOB selection allowing to select dates 1900, DOB called Surname, Next to profile 2 takes me back to logon screen | Closed
test 49 | Save button on profile page 2 | Not working |  |  | Open | send eamail to all
Test50 | Cancel Button on Profile Page 1 | Aborting |  |  | Open | Send email to all
test 51 | Why isnt there cancel button on profile page 2 |  |  |  | Open | Send email to all
test 52 | return button after removal | ABorting |  | I removed Deirdre1.Shanahn1 and all went well untik final screen to return and it aborts. Thinking this should take you back to logon screen | Open
Test 53 | Admin Screen |  |  | Lisa Sharp 4 times on the site - is this correct. Does thi mean that 4 people complained about her | Open
Test 54 | Admin Screen |  |  | What is the button beside the photo for. Looks like you can select the photo or the button | Open
test55 | Admin Screen - View Option | takes to view profile . I don’t know if we have time but Admin should not display the options to like /etc |  |  | Open
Test 66 | Logon Screen |  |  | Always Defaults to Lisa - no matter what ID you out in | Open

## Register
| open/closed | comment
logged on as existing user | closed | worked as expected - error "this email is already registered"
logged on as non-existing user with *.com | Closed | invalid email address
short password | closed | Error as expected - password too short

## meeting space
Open/Closed
logged on as Lisa.Sharp@gmail.com
Not allowing me to select Edit Profile | Open
Home not working | open
News not working | Open
Contact not working | Open
About not working | Open
Report Option | Open
Menu not working | Open

## Profile Page 1
new profile option | Email | Defaults to emails | Closed
new profile option | Email | Should it allow you to change emails | Open
new profile option | Nearest Town | Automatically selects town - should this be blank | Open
new profile option | Gender | Defaults to Femail ?? | Open
new profile option | Preferred Gender | Defaults ?? | Open
new profile option | Seeking age | Slide Bar not working | Open
new profile option | Distance I will travel | Slide Bar not working | Open
new profile option | Realtionshiop Love | allows user to select nothing | Open
new profile option | Update to Database | Email updated | Closed
new profile option | Update to Database | firstname updated | closed
new profile option | Update to Database | Surname Updated | Closed
new profile option | Update to Database | DOB updated | Closed
new profile option | Update to Database | nearest town updated | Closed
new profile option | Update to Database | gender updated | Closed
new profile option | Update to Database | prefered Gender Updated | Closed
new profile option | Update to Database | Relationshop type updated | Closed
new profile option | Cancel button | took me back to Meeting Space | Closed

## Reports
Weekly Update w/e 27 July | Open
Weekly Update w/e 03 Aug | Open
Final Project Report | Open
Introduction | Open | Update
High level functionality | Open | take from original and update
Web page mock ups | Open | need to update current mockups
Database tables | Open | Update if needed
User testing (how you reacted to the user tests from deliverable 5) | Open
Extras (any extra functionality that you added over the initial brief) | Open
Administration detail (how can we log on as administrator to your site) | Open
Sources (list any items such as images that you took from somewhere, showing the image and the original source) | Open
In particular, note any deviations from the original design | Open

## Testing Requirements
30 User profiles Set up | Open
10 Organizations | Open | Need to understand what is needed
Three staff members will test the functionality described in the Project
Three staff members will test the functionality described in the Project Overview, this will include:
Registering as users and creating profiles; | Open
Browsing users (without specific search terms); | Open
Searching for users (including each other); | Open
Observing the automatic suggestions; | Open
Connecting to each other | Open
Logging in as site administrator (your final report will need to describe how to do this, see below) | Open
The demo will be conducted using two different web browsers (we recommend Firefox and Google Chrome, but the group can decide); | Open
A final report using the headings described below needs to be uploaded to Moodle by August 5th | Open
additonal thoughts based on the testing exercise
1. Was there an index.html file? Was it obvious what the website was from the first page? | Open
1. What is the site for? Describe the industry that the site targets. | Open
1. How well did the individual registration section work? What happened when you put in malformed input (for example, mismatched passwords, wrong types, etc.)? | Open
1. Did the search function work? | Open
1. What was the “look and feel” of the site like? Was it pleasant to use or were there rendering problems and/or missing links? | Open

## Test Data Creation notes
| Test | Action on test Data to do test
Meeting Space | IF user selects someone - nothing happens unless the person they liked has liked them. | Make sure and create test data with Users who have already liked the person
Interested in Me | Please note following flow. System Match, Intereseted in me, Chat | if you say goodbye on any of these they will not appear again

## DatesGrade Structure
Section Marks Report 20% Usability 20% Registration 10% Profiles 10% Browse 10% Search 15% Auto-suggest 5% Administration 10% Extras Up 10% extra credit
1 | July 23rd |  | Work on website
12 | July 30th | Final product due August 5th | Work on website
Grading Structure
Mid term exam (May 30th): 20%
Design document (Sunday, June 24th): 20%
Database implementation (Sunday, July 1st): 5%
Prototype (Sunday, July 15th): 5%
Software Test Report (Sunday, July 22nd) 5%
Implementation (Sunday, August 5th): 40%
Documentation: 5%

## Functionality
Function # | Screen | Description
FN1 | HOME | Provide the user with home page which Displays the Option to Either Logon or Register
FN2 | Register | User can select Register from Logon Screen and will be navigated to Screen to enter Email and Password
FN3 | Reset Password | If User cannot remember password they have the option to select reset password from Logon Screen which will navigate them to screen to enter email and new password will be sent to email
FN4 | Meeting Space | When User is successful in Logging on they will be navigated to Meeting Space which is the HUB of the Dating Site and will display 5 features
Heading Navigate Bar at the top will display Name of the User and Allow them the option to Edit Profile, Edit Profile, Remove their Profile from the Site, Logout of the Site Match Finder - this is a spontaneous function which allows the user look for matches under different criteria than stored in their Profile. Facilitating the user if they are in a different location or indeed if they are looking for a different profile at this moment. This information is not stored in the Database
You are Chatting With Option Box - Provide details of chats you are having
Possible Matches Photos allowing me the option to Like/Maybe/Goodbye/Report (see FN5)
People Who Like Me - Displaying details of people who like my profile and may be interested in me
People Who I Like Details of all the people I have liked and that I may find a match
FN4.100 | Meeting Space/Edit Profile | Edit Profile allows user to create a new profile or edit exiting profile. User is asked to enter First Name , Surname, DOB, Nearest City/Town, Gender (allowing drop down option Male, Female, Transgender M-F or F-M ), Preferred Gender (same validation per Gender) Seeking Min Age Profile (using slide bar ), Seeking Max Age Profile(using slide bar), Distance User will travel (Using Distance bar) Relationship type (Love,Casual,Friendship,Relatioship - Radio Buttons). Validation limited due to drop down screens and radio buttons. Mix /Max Age is validated. Press Next to take user to Second Profile details screen (Personal Details Page2 FN4.2) or Cancel which brings user back to Meeting Space
FN4.101 | Meeting Space/Edit Profile | Edit Second Profile Page(Personal Details Page 2) Allows the user to load their Photograph, update some additional information in BIO box and select through radio buttons Hobbies which are - Music, Sport, Travelling, Sailing, Food, Work,Family,Cooking,Gym . SAVE
FN4.102 | Meeting Space/Remove Account | Remove Account will navigate the user to screen which clearly calls out the implications of removing account - everything will be removed . User is asked to Press Remove Account if they want to continue to Cancel (abort remove). If user selects Remove then ????? Adrian to advise what should happen as this aborts
FN4.103 | Meeting Space/Logoff | Logout - Navigates user to Log Out Screen providing the user with option Logoff or Cancel. Logoff will bring user to screen to confirm they really want to logout which bring user back to logon screen. Cancel will bring user to Meeting Space
FN4.104 | Meeting Space/Match Finder | This is a spontaneous option for the user to decide if they want to change some of their profile information to get meet a partner. The user is presented with screen Gender Preference, Preferred location, Relationship type, Interests, Seeking Age. All these use the drop down screen which limits the user to the Mandatory Choices.
FN4.105 | Meeting Space/Possible Matches | Will display list of people who may be a match for me User needs to click on the photos that they want to do an action with
FN4.106 | Meeting Space /Possible Matches Like Option | User can select photo of possible Match and Select the Like Button. This will remove the Photo of this person from Possible Matches to People I have liked View
FN4.107 | Meeting Space/Possible Matches View Option | User can select photo of possible Match and Select the View Button, this will navigate the user to the next screen to see details of the Person who is a possible Match for me(Described in FNXX)
FN4.108 | Meeting Space/Possible Matches Maybe Option | User can select photo of possible Match and Select the Maybe Button. This will display a question mark under the possible Match phot for future reference. Please note this person's photo needs to remain on possible matches box
FN4.109 | Meeting Space/Possible Matches Goodbye Option | User can select photo of possible Match and Select the Goodbye Button. This will remove the person from possible Matches and will not be displayed again
FN4.110 | Meeting Space/Possible Matches Report Option | If the User Notices Something offensive on another user profile they have the option to Report this person the Sysadmin team. Selecting Report will flag the Profile of that person for the SYSADMIN team to check
FN4.111 | Meeting Space/People Who Like Me | This section of the Meeting Space will provide me with Details of possible matches who liked my profile
FN4.112 | Meeting Space/People Who Like Me/like | User can select photo of person who liked my Profile . Select the Like Button. If both users have liked each other this will automatically initiate the chat line screen
FN4.113 | Chat Line | This screen is initiated from the meeting space screen. User can send message to proposed match and start conversations and visa versa
FN5.0 | Administrator Options | This option allows the Admin to manage the site.
FN5.101 | Administrator Options -View | Click Photo to view why this person was reported.
FN5.102 | Administrator Options -Suspend 1 Month | Click Photo to view why this person was reported.
FN5.103 | Administrator Options - BAR | Removes the option for the person to join out app ever again
FN5.104 | Administrator Options - Logout Option | Same functionality as FNS3.104

## Sheet6
Future Partner Website Project Status
Dating Pages | Page Link | Password | Basic Screen Layout Complete | Layout fully compelte | accessing Database | Updating Database | All buttons functioning | Validation Complete | Style Complete
Index.php | http://hive.csis.ul.ie/4065/group05/index.php |  | Yes | Yes | N/A | N/A | Yes | N/A | No
Logon.php | http://hive.csis.ul.ie/4065/group05/Logon.php |  | Yes | Yes | Yes | Yes | Yes | Yes | No
Register.php | http://hive.csis.ul.ie/4065/group05/Register.php |  | Yes | Yes | Yes | Yes | Yes | WIP | No
meetingspace.php | http://hive.csis.ul.ie/4065/group05/MeetingSpace.php |  | Yes | Yes | Yes | No | WIP | No | No
updateprofile.php | http://hive.csis.ul.ie/4065/group05/UpdateProfile.php |  | Yes | WIP | WIP | No | No | No | No
viewmatchprofile.php | http://hive.csis.ul.ie/4065/group05/ViewMatchProfile.php |  | Yes | WIP | WIP | N/A | N/A | No | No
chatline.php | http://hive.csis.ul.ie/4065/group05/ChatLine.php |  | Yes | WIP | No | No | No | No | No
matchfind.php | http://hive.csis.ul.ie/4065/group05/MatchFind.php |  | Yes | WIP | No | No | No | No | No
removeaccount.php | http://hive.csis.ul.ie/4065/group05/RemoveAccount.php |  | Yes | Yes | Yes | Yes | Yes | Yes | No
passwordreset .php | http://hive.csis.ul.ie/4065/group05/PasswordReset.php |  | Yes | WIP | No | No | No | No | No
adminscreen.php | http://hive.csis.ul.ie/4065/group05/AdminScreen.php |  | Yes | WIP | Np | No | No | No | No