## Home Page
| Solution | Open/Closed
lot of informaiton - | Maybe put in smaller boxes | Open
login | Working | closed
Register option | Working | Closed
Basic functionality of this Page only

## Testing Details
|  |  | Option | Comments | Action
Test1 |  | Logon Type email Deirdre.Shanahan@gmail.com | Forgot Password Option | Allowed me to enter email but did not receive email | Open
Test2 |  | Logon as Lisa Sharp Password welcomE01# | allowed me to logon and took me to Meeting Space | looks good so far | closed
Test 3 | logon Option | Logon as Carol.James@gmail.com password welcomE01# | Logon option | Brought me to meeting space but error because of Profile Screen 2 | closed
Test4 | Edit profile | Logon as Carol.James@gmail.com password welcomE01# | Logon Option/Meting Space. Edit profile | First screen works, second screen display but save not functioning | closed
test 5 | Edit profile | logon as Lisa Sharp | Logon Option/Meeting Space/ Edit profile | First screen work , second screen works until I press save and it abends error "Warning: getimagesize(): Filename cannot be empty in C:\Users\User\Documents\GitHub\WebProject\Web\UpdateProfile2.php on line 24" | closed
Test 6 | Edit profile | Logon as Carol.James@gmail.com Password WelcomeE01 | Logon Option/Meeting Space/ Edit profile | First screen working , second screen works until I Save Get error "Warning: getimagesize(): Filename cannot be empty in C:\Users\User\Documents\GitHub\WebProject\Web\UpdateProfile2.php on line 24" + Notice: Undefined index: check_list in C:\Users\User\Documents\GitHub\WebProject\Web\UpdateProfile2.php on line 62 | closed
Test 7 | select correct partner I want to meet | logon as Lisa Sharp | logon/Meeting Space | chatting with Paul even though she wants Female ? | Open | Bad Data in Data base
Test 8 | mathces found | Logon as Carol.James@gmail.com password welcomE01# | logon/Meeting Space | You are chatting with No Mathces Found | closed | Need clarify on message
Test 9 | see if I get the correct sex partner | Logon as Carol.James@gmail.com password welcomE01# | logon/Meeting Space | Matched with Male when she wants a female | Open | Checked again on 25 July - Still error open
TEst10 | buttons Funciton | Logon as Jacob.Newman@gmail.com Password welcomeE01 | logon/Meeting Space | none of the buttons in system functional yet | Open | Left Open Selected Like and got error
test11 | check like button | logon as Lisa Sharp and like Angela.Martin | logon/Meeting Space | worked | Closed
test12 | interested in me test | logon as as Angela.Marting - to check if Test 10 Lisa is someone interetsed in me |  | Angela appears as a match not interested in me | Closed | Lisa Flagged as interested in me
Test13 | remember login details | Logon Details remembering previous emails | Logon | not remembering Lisa | Closed | Adrian to check
test 14 | select someone I am interetsed in | meeting space select people I may be interested in | logon/Meeting Space | allows me to select | closed
test 15 | selected someone I like | Logged on as john.doe@gmail.com and liked Lucas | logon/Meeting Space | allowed me to select and view profile | closed
test 16 | view someone I am interested in and like them | Logged on as john.doe@gmail.com select someone I like and view profile and like on view profile | logon/Meeting Space | Aborted with error " A session had already been started - ignoring session_start() in C:\Users\User\Documents\GitHub\WebProject\Web\ViewMatchProfile.php on line 18" | Closed
Test 17 | Check if Interetsed in me works | logged on bella.walsh - Una nash interested in me | logon/meeting Space | Broke with error | closed | Check Database
Test 18 | check chat funtion |  |  |  | Open | ReDo test
test 19 | Cap off 100KB on Image |  |  |  | Open
test20 | Admin User needs to go directly to Admin Screen | logon as 16230124@studentmail.ul.ie |  | Logged on correctly. Got No Matches Found- Should this be there are no issues found ? Here is printed on left hand page why ? When I select buttons it breaks with error (Screen Shot sent to Niall) | Open
test21 | Admin User need to be able to look at all users reported | logon as 16230124@studentmail.ul.ie | to be created - Niall |  | Open
Test22 | admin useer need to be able to supend account | logon as 16230124@studentmail.ul.ie | to be created - Niall |  | Open
Test23 | Admins user need to be able to terminate account | logon as 16230124@studentmail.ul.ie | to be created - Niall |  | Open
Test24 | Admin need to be able to assign user as administrator | logon as 16230124@studentmail.ul.ie | to be created - Niall |  | Open
Test 25 | Admins need to be able view profile and make decisions on same
Test26 | reset password
Test27 | sql inection ???
Test28 | formats the same
Test29 | correct all the open tests
Test30 | Sys Admin - View Profile -
Test 32 | Wire up button functions for Like, etc. -> Adrian
Test 33 | Code "Return to Match Profile" -> Adrian
Test 34 | Match Profile - Fix issue with selecting user you are not already matched to
Test 35 | UpdateProfile - Improve Formatting and include Mary's Sliders -> Mary
Test36 | UpdateProfile2 - Improve Formatting
Test37 | Password Reset - Write code -> Adrian
test38 | Session control - Make sure users cant spoof site -> Adrian
test39 | Chatline - Include bad word logic ->Adrian
Test40 | AdminScreen - Write moderation code -> Nial
test41 | more Checks on Meeting Space | Logon as Jacob.Newman@gmail.com Password welcomeE01 |  | Meeting Spaces Showing Matches me with Carol James even though she only wants female partners, Hit View to View Carol Profile. Liked profile and got error | Open | Sent email to team

## Register
| open/closed | comment
logged on as existing user | closed | worked as expected - error "this email is already registered"
logged on as non-existing user with *.com | Closed | invalid email address
short password | closed | Error as expected - password too short

## meeting space
Open/Closed
logged on as Lisa.Sharp@gmail.com
Not allowing me to select Edit Profile | Open
Home not working | open
News not working | Open
Contact not working | Open
About not working | Open
Report Option | Open
Menu not working | Open

## Profile Page 1
new profile option | Email | Defaults to emails | Closed
new profile option | Email | Should it allow you to change emails | Open
new profile option | Nearest Town | Automatically selects town - should this be blank | Open
new profile option | Gender | Defaults to Femail ?? | Open
new profile option | Preferred Gender | Defaults ?? | Open
new profile option | Seeking age | Slide Bar not working | Open
new profile option | Distance I will travel | Slide Bar not working | Open
new profile option | Realtionshiop Love | allows user to select nothing | Open
new profile option | Update to Database | Email updated | Closed
new profile option | Update to Database | firstname updated | closed
new profile option | Update to Database | Surname Updated | Closed
new profile option | Update to Database | DOB updated | Closed
new profile option | Update to Database | nearest town updated | Closed
new profile option | Update to Database | gender updated | Closed
new profile option | Update to Database | prefered Gender Updated | Closed
new profile option | Update to Database | Relationshop type updated | Closed
new profile option | Cancel button | took me back to Meeting Space | Closed

## Reports
Weekly Update w/e 27 July | Open
Weekly Update w/e 03 Aug | Open
Final Project Report | Open
Introduction | Open | Update
High level functionality | Open | take from original and update
Web page mock ups | Open | need to update current mockups
Database tables | Open | Update if needed
User testing (how you reacted to the user tests from deliverable 5) | Open
Extras (any extra functionality that you added over the initial brief) | Open
Administration detail (how can we log on as administrator to your site) | Open
Sources (list any items such as images that you took from somewhere, showing the image and the original source) | Open
In particular, note any deviations from the original design | Open

## Testing Requirements
30 User profiles Set up | Open
10 Organizations | Open | Need to understand what is needed
Three staff members will test the functionality described in the Project
Three staff members will test the functionality described in the Project Overview, this will include:
Registering as users and creating profiles; | Open
Browsing users (without specific search terms); | Open
Searching for users (including each other); | Open
Observing the automatic suggestions; | Open
Connecting to each other | Open
Logging in as site administrator (your final report will need to describe how to do this, see below) | Open
The demo will be conducted using two different web browsers (we recommend Firefox and Google Chrome, but the group can decide); | Open
A final report using the headings described below needs to be uploaded to Moodle by August 5th | Open
additonal thoughts based on the testing exercise
1. Was there an index.html file? Was it obvious what the website was from the first page? | Open
1. What is the site for? Describe the industry that the site targets. | Open
1. How well did the individual registration section work? What happened when you put in malformed input (for example, mismatched passwords, wrong types, etc.)? | Open
1. Did the search function work? | Open
1. What was the “look and feel” of the site like? Was it pleasant to use or were there rendering problems and/or missing links? | Open

## Test Data Creation notes
| Test | Action on test Data to do test
Meeting Space | IF user selects someone - nothing happens unless the person they liked has liked them. | Make sure and create test data with Users who have already liked the person
Interested in Me | Please note following flow. System Match, Intereseted in me, Chat | if you say goodbye on any of these they will not appear again

## DatesGrade Structure
Section Marks Report 20% Usability 20% Registration 10% Profiles 10% Browse 10% Search 15% Auto-suggest 5% Administration 10% Extras Up 10% extra credit
1 | July 23rd |  | Work on website
12 | July 30th | Final product due August 5th | Work on website
Grading Structure
Mid term exam (May 30th): 20%
Design document (Sunday, June 24th): 20%
Database implementation (Sunday, July 1st): 5%
Prototype (Sunday, July 15th): 5%
Software Test Report (Sunday, July 22nd) 5%
Implementation (Sunday, August 5th): 40%
Documentation: 5%

## Sheet3
create Admin user
user profile has IS ADMINISTRATOR