## Sheet1
Future Partner Website Project Status
Dating Pages | Page Link | Basic Screen Layout Complete | Layout fully compelte | accessing Database | Updating Database | All buttons functioning | Validation Complete | Style Complete
Index.php | http://hive.csis.ul.ie/4065/group05/index.php | Yes | Yes | N/A | N/A | Yes | N/A | No
Logon.php | http://hive.csis.ul.ie/4065/group05/Logon.php | Yes | Yes | Yes | Yes | Yes | Yes | No
Register.php | http://hive.csis.ul.ie/4065/group05/Register.php | Yes | Yes | Yes | Yes | Yes | WIP | No
meetingspace.php | http://hive.csis.ul.ie/4065/group05/MeetingSpace.php | Yes | Yes | Yes | No | WIP | No | No
updateprofile.php | http://hive.csis.ul.ie/4065/group05/UpdateProfile.php | Yes | WIP | WIP | No | No | No | No
viewmatchprofile.php | http://hive.csis.ul.ie/4065/group05/ViewMatchProfile.php | Yes | WIP | WIP | N/A | N/A | No | No
chatline.php | http://hive.csis.ul.ie/4065/group05/ChatLine.php | Yes | WIP | No | No | No | No | No
matchfind.php | http://hive.csis.ul.ie/4065/group05/MatchFind.php | Yes | WIP | No | No | No | No | No
removeaccount.php | http://hive.csis.ul.ie/4065/group05/RemoveAccount.php | Yes | Yes | Yes | Yes | Yes | Yes | No
passwordreset .php | http://hive.csis.ul.ie/4065/group05/PasswordReset.php | Yes | WIP | No | No | No | No | No
adminscreen.php |  | Yes | WIP | Np | No | No | No | No