## Home Page
| Solution | Open/Closed
lot of informaiton - | Maybe put in smaller boxes | Open
login | Working | closed
Register option | Working | Closed

## Register
| open/closed | comment
logged on as existing user | closed | worked as expected - error "this email is already registered"
logged on as non-existing user with *.com | Closed | invalid email address
short password | closed | Error as expected - password too short

## meeting space
Open/Closed
logged on as Lisa.Sharp@gmail.com
Not allowing me to select Edit Profile | Open
Home not working | open
News not working | Open
Contact not working | Open
About not working | Open
Report Option | Open

## Profile Page 1
new profile option | Email | Defaults to emails | Closed
new profile option | Email | Should it allow you to change emails | Open
new profile option | Nearest Town | Automatically selects town - should this be blank | Open
new profile option | Gender | Defaults to Femail ?? | Open
new profile option | Preferred Gender | Defaults ?? | Open
new profile option | Seeking age | Slide Bar not working | Open
new profile option | Distance I will travel | Slide Bar not working | Open
new profile option | Realtionshiop Love | allows user to select nothing | Open
new profile option | Update to Database | Email updated | Closed
new profile option | Update to Database | firstname updated | closed
new profile option | Update to Database | Surname Updated | Closed
new profile option | Update to Database | DOB updated | Closed
new profile option | Update to Database | nearest town updated | Closed
new profile option | Update to Database | gender updated | Closed
new profile option | Update to Database | prefered Gender Updated | Closed
new profile option | Update to Database | Relationshop type updated | Closed
new profile option | Cancel button | took me back to Meeting Space | Closed

## Reports
Weekly Update w/e 27 July | Open
Weekly Update w/e 03 Aug | Open
Final Project Report | Open
Introduction | Open | Update
High level functionality | Open | take from original and update
Web page mock ups | Open | need to update current mockups
Database tables | Open | Update if needed
User testing (how you reacted to the user tests from deliverable 5) | Open
Extras (any extra functionality that you added over the initial brief) | Open
Administration detail (how can we log on as administrator to your site) | Open
Sources (list any items such as images that you took from somewhere, showing the image and the original source) | Open
In particular, note any deviations from the original design | Open

## Testing Requirements
30 User profiles Set up | Open
10 Organizations | Open | Need to understand what is needed
Three staff members will test the functionality described in the Project
Three staff members will test the functionality described in the Project Overview, this will include:
Registering as users and creating profiles; | Open
Browsing users (without specific search terms); | Open
Searching for users (including each other); | Open
Observing the automatic suggestions; | Open
Connecting to each other | Open
Logging in as site administrator (your final report will need to describe how to do this, see below) | Open
The demo will be conducted using two different web browsers (we recommend Firefox and Google Chrome, but the group can decide); | Open
A final report using the headings described below needs to be uploaded to Moodle by August 5th | Open
additonal thoughts based on the testing exercise
1. Was there an index.html file? Was it obvious what the website was from the first page? | Open
1. What is the site for? Describe the industry that the site targets. | Open
1. How well did the individual registration section work? What happened when you put in malformed input (for example, mismatched passwords, wrong types, etc.)? | Open
1. Did the search function work? | Open
1. What was the “look and feel” of the site like? Was it pleasant to use or were there rendering problems and/or missing links? | Open

## DatesGrade Structure
1 | July 23rd |  | Work on website
12 | July 30th | Final product due August 5th | Work on website
Grading Structure
Mid term exam (May 30th): 20%
Design document (Sunday, June 24th): 20%
Database implementation (Sunday, July 1st): 5%
Prototype (Sunday, July 15th): 5%
Software Test Report (Sunday, July 22nd) 5%
Implementation (Sunday, August 5th): 40%
Documentation: 5%